## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | release alert | When the patient is aggressive, the doctor can release the alert in the mobile app iDoctor. He has 5 seconds time to stop the alert, if it is a false alert. After this 5 seconds the other staff and the policestation will receive a message. At the end the doctor is able to record an entry in the patient document about the incident. | high | 50h | 35h | 32h | not started
2 | patient referral |  | medium | 80h |  |  | not started
3 | denial handling |  | medium | 70h |  |  | not started
4 | data validation |  | high | 40h |  |  | not started

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | high | 8 | 6 | 4 | work in progress
1.3 | 3 |  |  | All | Martin | high | 16 | 20 | 20 | done
1.4 | 4 |  |  | Database | Tom | low | 4 | 10 | 4 | cancelled
|  |  |  | Main Window | Jennifer | high | 8 | 6 | 5 | work in progress
1.1 | 1 | Skeletal Structure | Creating Person/Case Class and design the relation in between. | Database, Controller | Adrian Wyss | high | 16 | 16 | 0 | not started
1.2 | 2 | Event Interface | Create the event interface. Implement in previously designed Case Class. | Controller | Rene Vielgut | high | 2 | 2 | 0 | not started
1.3 | 3 | Alert Class | Realizing the Alert Class | Controller | Patrick Hirschi | high | 6 | 6 | 0 | not started
1.4 | 4 | TicToc | Creating a Countdown Class for the alert. | Controller | Patrick Hirschi | high | 4 | 4 | 0 | not started
1.5 | 5 | Test Class | Functional Test of our new Software | All | Maja Kelterborn | high | 2 | 2 | 0 | not started
1.6 | 6 | GUI | Creating a WebSurface for the first test of our Software. | UI | Rafael Kapp | medium | 18 | 18 | 0 | not started
1.7 | 7 | GUI-Test | Functional Test of our new Software | All | Saskia Basler | medium | 2 | 2 | 0 | not started
2.1 | 1 | Referral Class | Create Referral Class and implement the Event Interface | Controller | Patrick Hirschi | high | 30 | 30 | 0 | not started
2.2 | 2 | Person Class | Create the 3 classes that inherit from our Person Class. (Patient, Doctor, Contact Person) | Database, Controller | Rene Vielgut | high | 20 | 20 | 0 | not started
2.3 | 3 | Address Class | Create the Address Class that is used in our Person class. | Database, Controller | Rafael Kapp | medium | 10 | 10 | 0 | not started
2.4 | 4 | Clinic Class | Create the Clinic Class that is used in our Person class. | Database, Controller | Adrian Wyss | medium | 10 | 10 | 0 | not started
2.5 | 5 | Test Class | Functional Test of our new Software | All | Saskia Basler | medium | 5 | 5 | 0 | not started
2.6 | 6 | GUI-Test | Functional Test of our new Software | All | Maja Kelterborn | medium | 5 | 5 | 0 | not started
3.1 | 1 | Denial Class | Create Denial Class and implement the Event Interface | Controller | Adrian Wyss | high | 30 | 30 | 0 | not started
3.2 | 2 | Implementation | Implement Relations to other integrated classes, such as Person and Case. | Database, Controller | Rafael Kapp | high | 10 | 10 | 0 | not started
3.3 | 3 | Notification | E-Mail Notifier | All | Patrick Hirschi | medium | 20 | 20 | 0 | not started
3.4 | 4 | Test Class | Functional Test of our new Software | All | Saskia Basler | medium | 5 | 5 | 0 | not started
3.5 | 5 | GUI-Test | Functional Test of our new Software | All | Maja Kelterborn | medium | 5 | 5 | 0 | not started
4.1 | 1 | Treatment Class | Create Treatment Class and implement the Event Interface | Database, Controller | Patrick Hirschi | high | 6 | 6 | 0 | not started
4.2 | 2 | Medication Class | Create Medication Class (inherited from Treatment Class) | Database, Controller | Rene Vielgut | high | 6 | 6 | 0 | not started
4.3 | 3 | Implementation | Implement Relations to other integrated classes, such as Person and Case. | Database, Controller | Rafael Kapp | high | 8 | 8 | 0 | not started
4.4 | 4 | Validator Class | Create Data Validator Class | Controller | Rafael Kapp | high | 10 | 10 | 0 | not started
4.5 | 5 | Implementation | Implement in all other classes | All | Adrian Wyss | high | 6 | 6 | 0 | not started
4.6 | 6 | Test Class | Functional Test of our new Software | All | Saskia Basler | medium | 2 | 2 | 0 | not started
4.7 | 7 | GUI-Test | Functional Test of our new Software | All | Maja Kelterborn | medium | 2 | 2 | 0 | not started
7 Wochen / Sprint
|  | Tage | (7*5)/8.75 | 4 Sprints | [5 empty] | 8.75 | Anzahl Tage pro Sprint
[10 empty] | 70 | Stunden pro Sprint
|  |  | 8.75/6*8/1.75 = 6.666 | Stunden pro Person pro Sprint pro Woche | [5 empty] | 6 | Teammitglieder
[10 empty] | 1.75 | Anzahl Wochen pro Sprint | (8.75/5)
Zeitraum: Montag 2.12.2013 - 31.01.2014
|  |  | Zeitschätzung für Story | 240
|  |  | Zeitschätzung für Sprints | 280
|  |  | Meetings, GitHub, Daily Scrum | 40