## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | release alert | When the patient is aggressive, the doctor can release the alert in the mobile app iDoctor. He has 5 seconds time to stop the alert, if it is a false alert. After this 5 seconds the other staff and the policestation will receive a message. At the end the doctor is able to record an entry in the patient document about the incident. | high | 50h | 35h | 32h | not started
2 | patient referral | If the patient must be referred, the doctor can click on the referral button and enter information about: during time, diagnosis, external clinic or doctor, name of the doctor, is it a FU or a normal referral,… after click on the button "send referral" the input will be writen to a txt. file. The referral is also visible in the patientview. | medium | 80h |  |  | not started
3 | denial handling | When the patient denies drugs the doctor can enter when the patient does it and what drug. This will then be visible in the patientview. | medium | 70h |  |  | not started
4 | data validation |  | high | 40h |  |  | not started

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Skeletal Structure | Create Packages and structure of the application | Database, Controller | Rafael Kapp | high | 16 | 16 | 5 | finished | Total (exkl. Test)
1.2 | 2 | Event Interface | Event interface for further classes. | Controller | Rafael Kapp | high | 2 | 2 | 1 | finished
1.3 | 3 | GUI (index,alert) | Creating GUI (indexView, alertView) | UI | Rafael Kapp | high | 18 | 18 | 20 | finished
1.4 | 4 | Alert Class | Realizing the Alert Class | Controller | Patrick Hirschi | high | 6 | 6 | 6 | finished
1.5 | 5 | TicToc | Creating a Countdown Class for the alert. | Controller | Patrick Hirschi | high | 4 | 4 | 5 | finished
1.6 | 6 | DatabaseHandler | Create a DatabaseHandler to handle persistent data | Database | Rafael Kapp | high | 5 | 7 | 10 | finished
1.7 | 7 | Test Class | Testing the alert class | All | Adrian Wyss | high | 2 | 5 | 0 | not started
1.8 | 8 | GUI-Test | GUI-Test (klicking, sliding, logic,...) | All | Saskia Basler | medium | 2 | 5 | 0 | not started | 47
2.1 | 1 | Referral Class | Create Referral Class and implement the Event Interface | Controller | Maja Kelterborn | high | 20 | 20 | 10 | finished
2.2 | 2 | GUI (referral) | Creating GUI (referral) | UI | Maja Kelterborn | high | 10 | 10 | 10 | finished
2.3 | 3 | Denial Class | Create Denial Class and implement the Event Interface | Controller | Saskia Basler | high | 20 | 20 | 8 | finished
2.4 | 4 | GUI (denial) | Creating GUI (denial) | UI | Saskia Basler | high | 20 | 20 | 10 | finished
2.5 | 5 | Person Class | Create the 3 classes that inherit from our Person Class. (Patient, Doctor, Contact Person) | Database, Controller | Rafael Kapp | high | 20 | 20 | 4 | finished
2.6 | 6 | GUI (Person) | Creating GUI (Person) | UI | René Vielgut | high | 15 | 13 | 12 | finished
2.7 | 7 | Address Class | Create the Address Class that is used in our Person class. | Database, Controller | Rafael Kapp | medium | 10 | 10 | 1 | finished
2.8 | 8 | Test Class | Functional Test of our new Software | All | Saskia Basler | medium | 5 | 5 | 0 | not started
2.9 | 9 | GUI-Test | GUI-Test (klicking, sliding, logic,...) | All | Maja Kelterborn | medium | 5 | 5 | 0 | not started | 55
3.1 | 1 | Clinic Class | Create the Clinic Class that is used in Person and Denial class. | Database, Controller | Adrian Wyss | medium | 20 | 20 |  | started
3.2 | 2 | Treatment Class | Create Treatment Class and implement the Event Interface | Database, Controller | Patrick Hirschi | high | 20 | 20 |  | not started
3.3 | 3 | Medication Class | Create Medication Class (inherited from Treatment Class) | Database, Controller | Adrian Wyss | high | 6 | 6 |  | not started
3.4 | 4 | Implementation | DatabaseHandler (Medication and Treatment) | Database, Controller | Rafael Kapp | high | 8 | 8 |  | not started
3.5 | 5 | Test Class | Test of medication implementation via Denial and Treatment classes | All | Adrian Wyss | medium | 2 | 2 |  | not started
3.6 | 6 | Test Class | Testing the Treatment class | All | Saskia Basler | medium | 5 | 5 |  | not started
3.7 | 7 | GUI-Test | GUI-Test (klicking, sliding, logic,...) | All | Maja Kelterborn | medium | 7 | 7 |  | not started

## time schedule (quick and dirty)
7 Wochen / Sprint
Tage | (7*5)/8.75 | 4 Sprints | 8.75 | Anzahl Tage pro Sprint
|  |  | 70 | Stunden pro Sprint
| 8.75/6*8/1.75 = 6.666 | Stunden pro Person pro Sprint pro Woche | 6 | Teammitglieder
|  |  | 1.75 | Anzahl Wochen pro Sprint | (8.75/5)
Zeitraum: Montag 2.12.2013 - 31.01.2014
| Zeitschätzung für Story | 240
| Zeitschätzung für Sprints | 280
| Meetings, GitHub, Daily Scrum | 40